## Guide
Summary Sheet
|  | Purpose of the Summary Sheet | The Summary sheet provides a consolidated, at‑a‑glance view of all actions across every Hazard Study Record Sheet for the Project (contained in the workbook). It automatically displays only the actions with a Status of: • Open • In Progress • Under Review This allows study teams, project managers, and action owners to quickly identify outstanding actions without manually checking each record sheet.
|  | How the Summary Sheet Works | Each individual Hazard Study Record sheet (e.g., Record_1, Record_2, Record_3…) contains the action items generated during that specific HAZID or HAZOP study. When an action is created or updated on a Record sheet, the Summary sheet automatically collects: • The Record Sheet name • Study Type (HAZID or HAZOP) • Study Name • Action ID • Action Description • Actioner Name • Target Date • Status Only actions with the statuses listed above appear on the Summary sheet. Actions marked Closed automatically drop off the summary.
|  | What Users Can Do on the Summary Sheet | You can: • View all open/active actions in one place. • Sort or filter by: ○ Study Type ➤ Study Name ➤ Actioner Name ➤ Target Date ➤ Status • Identify overdue actions (these appear with conditional red highlighting). • Confirm action ownership and required deadlines. • Export a filtered list for meetings, reviews, or management reporting. You cannot: • Edit action details directly on the Summary sheet. • All modifications must be made in the originating Record sheet. This prevents inconsistencies and keeps the workbook compliant with the study documentation process.
|  | How to Update an Action | Identify the action’s Record Sheet name from column A of the Summary. • Navigate to that sheet via the bottom tab. • Locate the action row. • Update: ○ Status ○ Target Date ○ Action Description ○ Actioner Name ○ Any other field as required The Summary sheet will update automatically.
Record Sheets
Common to all Record Sheet Headers
|  | Record Sheet Name | Automatically populated no input required.
|  | Study Type | Choose the type of risk study being performed: HAZID or HAZOP. (Drop down list provided) "Important to ensure field is completed first to set the worksheet fields".
|  | Study Name | What it is: The formal name of the HAZID/HAZOP. Examples: • “H-000010 Gordon #1 2026 Outage - MIV Tasmania Transport" • “H-000011 Fisher 2026 Tunnel Inspection"
|  | Date | The date(s) the workshop is held. Example: Enter as "30/01/2026"
|  | Stage of project | What lifecycle stage you are in. (Drop down list provided)
|  | Tier of Study | Defines the type of review based on corporate risk governance. (Drop down list provided) Typically: • Tier 1: Higher-risk “Study led by trained Facilitator” • Tier 2: Lower-risk “Study can be led by project team untrained Facilitator”
|  | References used | List key technical documentation relied upon during the study. Examples: • P&IDs • Layout drawings • Process flow diagrams (PFDs) • Operating manuals • Design basis documents • Hazardous chemical SDSs • Australian / ISO standards • Previous HAZOP or incident reports Example entry: “P&ID 300-P-051 Rev C, AS/NZS 3000, OEM data sheet for pump P-102.”
|  | Terms of Reference | A short, clear statement describing why the study is being conducted and what it covers. Should answer, why is this study needed? What part of the project or system does it apply to? Examples: • “To systematically identify process hazards and operability issues in the new ammonia storage system.” • “To review design intent, deviations, and safeguards for the commissioning phase.” • “To ensure hazards are identified early for the detailed design of the water pipeline upgrade.”
|  | Objectives of the HAZID/HAZOP | State the main aims the study intends to achieve. Typical objectives: • Identify hazards and potential causes. • Assess potential consequences to people, environment, and assets. • Review effectiveness of existing controls. • Generate actions to reduce risk to ALARP. • Confirm that design assumptions remain valid. Example: “To identify safety, environmental, and operational hazards associated with the proposed plant modifications and ensure risk control measures are adequate.”
|  | Boundaries and interfaces | What’s inside and outside the scope. Also system handovers, integration points, or adjacent systems. Include: • Physical boundaries (e.g., “Tank 1 to Pump 3 including pipework”) • Operational boundaries (e.g., “Start-up only, steady-state, no shutdown review”) • Interfaces (e.g., “Interfaces with power supply system and SCADA network”) Examples: • Inside scope: New chlorination line, injection pump, and dosing skid • Outside scope: Existing storage tank and building structure • Interfaces: Electrical supply, control room SCADA, chemical delivery trucks
|  | Assumptions and exclusions | Anything taken as true, or intentionally not reviewed. Examples of assumptions: • “Normal operating conditions assumed.” • “Operator competence based on current training matrix.” • “Electrical isolation points installed as per design.” Examples of exclusions: • “Maintenance activities not reviewed.” • “Civil/structural risks excluded—covered in separate CCR.” • “Emergency response reviewed under independent ERP study.”
|  | Facilitator | What it is: The independent or appointed person leading the study. Example entries: • “John Smith - Trained Facilitator” • “Jane Smith - Project Team Facilitator”
|  | Scribe | Person responsible for recording minutes, deviations, actions, and results.
|  | Attendees (team members & disciplines) | Who is participating and what discipline they represent. HAZID/HAZOP is multidisciplinary. Examples of disciplines: • Process engineering • Operations • Maintenance • Electrical • Instrumentation & control • Safety • Environmental • Project engineering • Construction • Environmental • Contractor reps • OEM specialists Example entry: “Operations (John Smith, Jane Smith), Mechanical Engineer (John Smith) , Electrical Technician (Jane Smith), WHS Representative (John Smith), Enviro Representative (Jane Smith), Contractors {ABC Construction (John Smith, Jane Smith)}, {ABC Electrical (John Smith, Jane Smith)}.”
HAZID
|  | ID | Unique Identifier (Automatically populated based on Study Type)
|  | Hazard Category | A high-level classification to group hazards. (Drop down list provided)
|  | (blank) | Blank column due to the HAZID/HAZOP study type. No input required
|  | Hazard/Opportunity Description | A concise description of the hazard/opportunity (the thing with the potential to cause harm or provide an improvement). Good practice: Be specific and observable. Examples: • “Unprotected edges at mezzanine level (3 m drop).” • “Stored energy in hydraulic lines of press.” • “Handling 25 kg concrete bags ≥ 20 times/day.”
|  | Potential Causes | Conditions or failures that could lead to the hazard manifesting. Examples: • Inadequate edge protection; missing guardrail mid-rail. • Isolation procedure not followed; residual pressure. • Poor housekeeping; weather (wet surfaces); inadequate lighting. • Inadequate training or supervision; time pressure. Tip: Capture both technical and organisational causes.
|  | Potential Consequences | Reasonable worst-case outcomes if the hazard is realised. Examples: • Fall from height → major injury, fatality. • Arc flash → burns, hearing damage, fire. • Chemical exposure → acute toxicity, chronic illness. • Manual handling → musculoskeletal disorder (MSD), lost-time injury (LTI). Tip: Consider people, environment, assets, reputation, and legal impacts as applicable.
|  | Existing Controls | Controls already in place (describe exactly what exists, not what’s planned). Use the Hierarchy of Controls when listing: • Elimination: Not performing task during live operation. • Substitution: Using less hazardous chemical. • Engineering: Guardrails, machine guarding, interlocks, ventilation, fixed platforms. • Administrative: SWMS/Risk Register, permits to work, isolation procedures, training, supervision, signage, scheduling. • PPE: Harness & lanyard, arc-rated clothing, respirators, gloves, eye protection. Example entry: “Fixed guardrail with top/mid/Toe; PTW for work at height; certified anchor points; workers trained in WAH; daily pre-start checks.”
|  | Impact Category | What is the primary impact of the hazard, before controls, aligned to the WHS risk matrix. (Drop down list provided) Refer: IBRM Procedure
|  | Probability Category | What is the qualitative likelihood rating before controls, aligned to the WHS risk matrix. (Drop down list provided) Refer: IBRM Procedure
|  | Risk Rating | The combined Consequence × Likelihood per your risk matrix; can be a colour band and/or value. (Automatically calculated based on Impact and Probability Categories)
|  | Recommendations | Further actions to reduce risk as low as reasonably practicable (ALARP). Make them SMART: Specific, Measurable, Achievable, Relevant, Time-bound. Examples by hierarchy: • Elimination: Prefab components at ground. • Substitution: Switch to lower-voltage tools where feasible. • Engineering: Install self-closing gates at ladder access; fit non-slip grating; add local exhaust ventilation. • Administrative: Update isolation procedure to include air bleed; increase supervisor verification; fatigue management roster changes; add toolbox talk topic. • PPE: Upgrade to cut level C gloves; introduce face shields for decanting. Tip: Avoid vague phrases like “remind staff” without a concrete mechanism.
|  | Action Required | Short status cue on whether further work is needed. (Drop down list provided)
|  | Action Description | The exact task to implement the recommendation. Examples: • “Install self-closing gate at Mezz A NW ladder access (AS 1657 compliant).” • “Revise LOTO SOPO to add hydraulic energy bleed step; retrain maintenance crew.” • “Procure and fit fall restraint anchor line on draft tube stop log slot; certify by accredited inspector.”
|  | Actioner Name | The person/role accountable for the action. Format suggestions: Full name and role or contractor company. Example: “John Smith - Maintenance Supervisor.”
|  | Target (Due) Date | The date the action must be completed. Tips: Consider the risk priority and project schedule. Example: Enter as "30/01/2026"
|  | Action Status | Current state of the action or hazard record. (Drop down list provided) • Open: Action has been created but no work has commenced. • In Progress: Work has commenced, but action is not yet complete. • Under Review: Action completion is pending verification or approval. • Closed: Completed - Will not appear on Summary Sheet.
|  | Added to Risk Register | Indicates whether this hazard has been escalated or captured in the project, site or operational risk registers. When to mark Yes: • Risks with broader/systemic implications. • Risks exceeding project authority/tolerance. • Enterprise-level trends or repeating high-severity hazards. Example: Yes - PRR-2026-103. (Provide minimal but sufficient detail to connect this hazard to the applicable register), always commence with "Yes - ".
HAZOP (technical and construction based details provided)
|  | ID | Unique Identifier (Automatically populated based on Study Type)
|  | Description / Node | The system section being analysed. • Technical HAZOP: Node aligned to P&ID segments (or similar) or equipment (e.g., “Pump P 101 discharge to HX 01”). • Construction HAZOP: Node aligned to activities/temporary works/areas/phase (e.g., “Excavation Bay 4 - 3 m deep with shoring”). Examples: • Technical: “TK 04 level control loop (LIC 401 → LV 401)” • Construction: “Temporary LV power distribution (Switch room fit out)”
|  | Guideword | Prompt word to explore deviations. • Technical guidewords (typical): No / More / Less / Reverse / Part of / As well as / Other than / Early / Late / Before / After • Construction specific additions: Wrong place / Wrong time / Out of sequence / No access / No egress / No permit / No isolation / Live adjacent / Unstable / Weather affected / Congested / Unexpected service / Untrained / Poor visibility Examples: • Technical: No, More, Reverse • Construction: Out of sequence, No isolation, More wind Refer: Hazard and Operability Study - Preparation Guide for full lists.
|  | Deviation | The undesired state produced by Guideword + Parameter. • Technical parameters: flow, pressure, temperature, level, composition, phase, mixing, reaction rate. • Construction parameters: access/egress, stability/support, load, lift radius, ground bearing, isolation state, utilities, ventilation, lighting, sequencing, traffic, weather limits, supervision, permits. Examples: • Technical: “No flow to HX 01”; “More pressure in line 204”; “Reverse flow through NRV” • Construction: “No isolation of LV board before tie in”; “More wind than lift limit”; “Out of sequence decking under live edge”
|  | Possible Causes | Why the deviation could occur (technical, human, organizational, external). Examples: • Technical: Valve left closed; pump trip; blocked strainer; transmitter drift; control loop tuning error; power loss; instrument air failure; wrong setpoint. • Construction: Permit not raised/approved; incorrect lift radius; outrigger on unverified fill; inaccurate BYD; weather change; subcontractor overlap; poor comms; temporary works not installed per design; back feed on temp power.
|  | Consequences | Reasonable worst case outcomes. Examples: • Technical: Overpressure → rupture → loss of containment; thermal runaway; product contamination; pump cavitation/damage; environmental release; personnel exposure. • Construction: Crane tip/strike; trench collapse; fall from height; plant–pedestrian collision; service strike (gas/water/HV); fire/explosion (hot works); stormwater pollution; delay and rework.
|  | Existing Safeguards | Prevention/mitigation in place now (don’t list future actions here). • Technical examples: interlocks; high trips; alarms; NRV; double isolation; relief to flare; bunds; SOP; operator rounds; maintenance regime. • Construction examples: Certified shoring; edge protection; exclusion zones; lift plan; competent riggers/doggers; anemometer; mats sized to geotech; PTW (hot work, CS, excavation, energisation); DBYD + potholing; temp power RCDs & lockable isolators; ventilation & gas monitors; traffic management plan; night work lighting plan; toolbox brief.
|  | Impact Category (optional) | What is the primary impact of the hazard, before controls, aligned to the WHS risk matrix. (Drop down list provided) • Optional field. Not required for HAZOPs but can be used to help prioritise actions where useful. Refer: IBRM Procedure
|  | Probability Category (optional) | What is the qualitative likelihood rating before controls, aligned to the WHS risk matrix. (Drop down list provided) • Optional field. Not required for HAZOPs but can be used to help prioritise actions where useful. Refer: IBRM Procedure
|  | Risk Rating (optional) | The combined Consequence × Likelihood per your risk matrix; can be a colour band and/or value. (Automatically calculated based on Impact and Probability Categories, where utilised)
|  | Recommendations | Additional controls to reduce risk ALARP, following the hierarchy (Eliminate ↓ Substitute ↓ Engineer ↓ Admin ↓ PPE). • Technical examples: Install low flow trip; add independent high pressure switch; alarm rationalisation; relief sizing verification; add quench; modify setpoints; improve sampling/analytics. • Construction examples: Upgrade shoring class; enlarge outrigger mats; add self closing gates; fit hook anemometer; revise lift plan & wind cut out; mandatory potholing; add spotter role; re sequence to avoid interface clashes; introduce isolation checklists; add ventilation ducting and continuous gas monitoring.
|  | Action Required | Short status cue on whether further work is needed. (Drop down list provided)
|  | Action Description | The doable task to implement the recommendation-precise, verifiable. Examples: • Technical: “Install independent high pressure switch (PSH 204) with trip on P 101; proof test 6 monthly; update shutdown cause and effect.” • Construction: “Supply & fit calibrated anemometer at hook; revise LP CR 07 with 9 m/s stop threshold; brief lift crew; supervisor to verify with photos prior to first lift.”
|  | Actioner Name | Accountable person. Examples: Name + Role Example entry: Jane Smith - Site Manager
|  | Target (Due) Date | The date the action must be completed. Tips: Consider the risk priority and project schedule. Example: Enter as "30/01/2026"
|  | Action Status | Current state of the action or hazard record. (Drop down list provided) • Open: Action has been created but no work has commenced. • In Progress: Work has commenced, but action is not yet complete. • Under Review: Action completion is pending verification or approval. • Closed: Completed - Will not appear on Summary Sheet.
|  | Added to Risk Register | Indicates whether this hazard has been escalated or captured in the project, site or operational risk registers. When to mark Yes: • Risks with broader/systemic implications. • Risks exceeding project authority/tolerance. • Enterprise-level trends or repeating high-severity hazards. Example: Yes - PRR-2026-103. (Provide minimal but sufficient detail to connect this hazard to the applicable register), always commence with "Yes - ".

## WHS Risk Matrix (hidden)
CONSEQUENCE
| Probability \ Impact | 1. Insignificant | 2. Minor | 3. Moderate | 4. Major | 5. Extreme | 6. Catastrophic
LIKEIHOOD | 7. Almost Certain | 7 | 14 | 21 | 28 | 35 | 42
| 6. Likely | 6 | 12 | 18 | 24 | 30 | 30
| 5. Possible | 5 | 10 | 15 | 20 | 25 | 30
| 4. Unlikely | 4 | 8 | 12 | 16 | 20 | 24
| 3. Rare | 3 | 6 | 9 | 12 | 15 | 18
| 2. Extremely Rare | 2 | 4 | 6 | 8 | 10 | 12

## Lists (hidden)
HazardCategoryList | ReviewTypeList | ActionTypeList | LIKEIHOOD | LIKEIHOODScore | CONSEQUENCE | CONSEQUENCEScore | ActionStatus
Commercial / Legal | Audit | Administrative | Almost Certain | 7 | Insignificant | 1 | Closed
Controls/Automation | Bow-Tie Analysis | Engineering | Likely | 6 | Minor | 2 | For Review
Electrical | Construction Study | Management of Change | Possible | 5 | Moderate | 3 | In Progress
Environmental | Design / Engineering Review | Procedural | Unlikely | 4 | Major | 4 | Open
Finance / Cost Control | Change Management (MOC / Process / Operations / Scope) | Procurement | Rare | 3 | Extreme | 5
ICT / Cybersecurity | Functional Safety Assessment | Testing | Extremely Rare | 2 | Catastrophic | 6
Instrumentation | General / Periodic Review | Training
Maintenance | HAZID | Verification
Mechanical | HAZOP
Operations | Incident / Near-Miss Investigation
Political / External | Inspection
Process | Layer of Protection Analysis (LOPA)
Procurement | Lessons Learned
Procurement / Supply Chain | Operational Readiness (PSSR)
Project | Quantitative Risk Assessment (QRA)
QA/QC | Reliability / Failure Mode Analysis (FMEA / FMEDA)
Stakeholders | Safety in Design (SiD)
WHS | Task Risk Assessment

## Summary
"Hazard Study" Open, Pending and Under Review Action Summary
Record Sheet | Study Type | Study Name | ID | Action Description | Actioner Name | Target Date | Status

## Record_1
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: ← Select 1 to hide the "Study Information" rows, helps visually during the study presentation, select 2 to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_2
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_3
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_4
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_5
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_6
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_7
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_8
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_9
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_10
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_11
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_12
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_13
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_14
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_15
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_16
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_17
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_18
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_19
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_20
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_21
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_22)
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_23
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_24
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_25
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_26
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_27
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_28
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_29
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_30
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_31
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_32
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_33
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_34
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_35
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_36
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_37
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_38
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_39
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_40
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_41
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_42
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_43
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_44
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_45
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_46
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_47
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_48
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_49
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register

## Record_50
Hazard Study (Unified HAZID / HAZOP) Record Sheet -
NOTE: Press 1 ← to hide the "Study Information" rows, helps visually during the study presentation, Press 2 ← to unhide
Study Information | Record Sheet Name |  |  |  | #VALUE!
Study Type
Study Name
Date
(Hazard Study) Project Phase
Tier of Study
References used
Terms of Reference
Objectives of the HAZID/HAZOP
Boundaries and interfaces
Assumptions and exclusions
Facilitator
Scribe
Attendees (team members & disciplines)
NOTE: F2 Selected "Study Type" adjusts the "Study Record Register" output view below
Study Record Register | ID | Description / Node | Guideword | Deviation | Possible Causes | Consequences | Existing Safeguards | Impact Category (optional) | Probability Category (optional) | Risk Rating (optional) | Recommendations | Action Required | Action Description | Actioner Name | Target (Due) Date | Action Status | Added to Risk Register